## PROJECT PLAN
PROJECT PLAN( SignConnect ) Objectives: Build the next bi | time axis 2024-01-01 to 2024-06-05
Phases | Action item/Deliverables | Lead | Start Date | End Date | Status
Phase 1 - Deffine the Problem | bar: 2024-01-01 to 2024-04-18
| Introduction to Project | Isaac | 2424-01-24 | 2024-02-04 | Done
| Background of Study | Isaac | 2024-02-04 | 2024-02-17 | Done
| Objectives | Isaac | 2024-02-11 | 2024-02-24 | Done | 2024-01-01: Done; 2024-01-02: Done; 2024-01-03: Done; 2024-01-04: Done; 2024-01-05: Done; 2024-01-06: Done; 2024-01-07: Done
| Review Of Related Work | Isaac | 2024-03-04 | 2024-03-15 | In Progress | 2024-01-17: In Progress; 2024-01-18: In Progress; 2024-01-19: In Progress; 2024-01-20: In Progress; 2024-01-21: In Progress; 2024-01-22: In Progress; 2024-01-23: In Progress; 2024-01-24: In Progress; 2024-01-25: In Progress; 2024-01-26: In Progress; 2024-01-27: In Progress
Phase 2 - Design | bar: 2024-01-01 to 2024-04-18
| Proposed Methodology | Isaac & Etornyo | 2024-03-16 | 2024-03-29 | Done | 2024-01-09: Done; 2024-01-28: Done; 2024-01-29: Done; 2024-01-30: Done; 2024-01-31: Done; 2024-02-01: Done; 2024-02-02: Done; 2024-02-03: Done; 2024-02-04: Done; 2024-02-05: Done; 2024-02-06: Done; 2024-02-07: Done; 2024-02-08: Done; 2024-02-09: Done; 2024-02-10: Done
| Tools | Isaac & Etornyo | 2024-03-16 | 2024-03-18 | Done | 2024-01-28: Done; 2024-01-29: Done; 2024-01-30: Done
| Block Diagrams | Isaac & Etornyo | 2024-03-18 | 2024-03-19 | Done | 2024-01-30: Done; 2024-01-31: Done
| ER Diagrams | Isaac & Etornyo | 2024-03-22 | 2024-03-23 | In Progress | 2024-02-03: In Progress; 2024-02-04: In Progress
| Pipeline | Isaac & Etornyo | 3/34/2024 | 2024-03-27 | In Progress
| Flowchart | Isaac & Etornyo | 2024-03-26 | 2024-03-27 | Behind | 2024-02-07: Behind; 2024-02-08: Behind
| Mockups/Wireframes | Isaac & Etornyo | 2024-03-30 | 2024-03-29 | In Progress
Phase 3 | bar: 2024-01-01 to 2024-04-18
| Familiarization with Models & Stack | Etornyo | ####### | ####### | In Progress
Phase 4 - Development | bar: 2024-01-01 to 2024-04-18
| Actual Implementation | Etornyo | 2024-05-12 | 2024-07-21 | In Progress | 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress; 2024-03-31: In Progress; 2024-04-01: In Progress; 2024-04-02: In Progress; 2024-04-03: In Progress; 2024-04-04: In Progress; 2024-04-05: In Progress; 2024-04-06: In Progress; 2024-04-07: In Progress; 2024-04-08: In Progress; 2024-04-09: In Progress; 2024-04-10: In Progress; 2024-04-11: In Progress; 2024-04-12: In Progress; 2024-04-13: In Progress; 2024-04-14: In Progress; 2024-04-15: In Progress; 2024-04-16: In Progress; 2024-04-17: In Progress; 2024-04-18: In Progress
| Testing & Evaluation | Etornyo | 2024-05-18 | 2024-07-21 | Not started | 2024-03-31: Not started; 2024-04-01: Not started; 2024-04-02: Not started; 2024-04-03: Not started; 2024-04-04: Not started; 2024-04-05: Not started; 2024-04-06: Not started; 2024-04-07: Not started; 2024-04-08: Not started; 2024-04-09: Not started; 2024-04-10: Not started; 2024-04-11: Not started; 2024-04-12: Not started; 2024-04-13: Not started; 2024-04-14: Not started; 2024-04-15: Not started; 2024-04-16: Not started; 2024-04-17: Not started; 2024-04-18: Not started
| Building UI | Isaac | 2024-05-23 | 2024-07-21 | Not started | 2024-04-05: Not started; 2024-04-06: Not started; 2024-04-07: Not started; 2024-04-08: Not started; 2024-04-09: Not started; 2024-04-10: Not started; 2024-04-11: Not started; 2024-04-12: Not started; 2024-04-13: Not started; 2024-04-14: Not started; 2024-04-15: Not started; 2024-04-16: Not started; 2024-04-17: Not started; 2024-04-18: Not started
Phase 5 - Execution | bar: 2024-01-01 to 2024-04-18
| Deployment | Etornyo | 2024-07-22 | 2024-07-30 | Not started
| Conclusion & Recommendation | Isaac & Etornyo | 2024-08-01 | 2024-08-09 | Not started

## Chat GPT Project Board
Project Board Objective: Provide Update On VacAI | time axis 2024-02-18 to 2024-06-05
Task Name | Problem Stage | Assigned To | Priority | Resources | Start Date | End Date | Status
Define Target Audience & Customer Value | 1. Discover | Me | High | Google + ChatGPT | 2024-03-01 | 2024-03-09 | Behind | 2024-03-01: Behind; 2024-03-02: Behind; 2024-03-03: Behind; 2024-03-04: Behind; 2024-03-05: Behind; 2024-03-06: Behind; 2024-03-07: Behind; 2024-03-08: Behind; 2024-03-09: Behind
Create Project Board | 2. Define | Me | High | ChatGPT + Google Sheets | 2024-02-25 | 2024-03-01 | In Progress | 2024-02-25: In Progress; 2024-02-26: In Progress; 2024-02-27: In Progress; 2024-02-28: In Progress; 2024-02-29: In Progress; 2024-03-01: In Progress
Low
Low
Medium
Medium
Medium
High
High
High
High
High
High
High
High
High